## Mutual Action Plan - SaaS (hidden)
MUTUAL ACTION PLAN |  |  | VALTRON & CBRIGHT G5 DEAL
What is this? We like to use these non-binding planners to stay ahead of the curve and make the process as smooth as possible for all parties. Feel free to share with anyone in your org. |  |  | Valtron Factory Initiative Kick off |  | 2023-08-08 | Jump to Team members
|  |  | First Revenue (estimated date) |  | 2023-09-19
|  |  | First milestone completed (estimated date) |  | 2023-04-24 | Questions?
|  |  | Go Live (estimated date) |  | 2023-07-21 | Call or email Tom W anytime
|  |  | Days to Go Live (calculated) |  | 63 | 503-415-1428, tom@cbright.com
|  |  | Typical Process Length (days) |  | 76
Target Date | Done | Days ⤵ | Milestone | Owner (Valtron) | Owner (Cbright) | Outcome / Notes
2023-04-24 | TRUE |  | Intros & fit | Paul | Tom | Discuss business challenges /opportunities & identify where Valtron can help
2023-04-28 | TRUE | 4 | Establish use case(s) |  |  | Deep dive into how Valtron's G5 network would reduce contractor churn at Cbright
2023-05-02 | TRUE | 2 | Present business case |  |  | Get feedback on the business case and present our proposal
2023-05-30 | TRUE | 20 | Preflight |  |  | Work with Cbright's technical team and identify potential integration or infrastructure issues in advance
2023-06-27 | TRUE | 20 | Final negotation & signatures |  |  | Contracts / payment details finalized.
2023-07-06 | TRUE | 7 | Implementation / integration |  |  | Cbright team works with Valtron counterparts to integrate & test implementation
2023-07-13 | TRUE | 5 | Onboarding |  |  | Team training & Customer Success plan finalized
2023-07-21 | FALSE | 6 | GO LIVE: Flip the switch!
2023-08-08 |  | 12 | Valtron Factory Initiative Kick off |  | EXTERNAL | EXTERNAL
2023-09-19 |  | 30 | First Date of Value |  |  | $500K savings in first 30 days
2024-05-28 |  | 180 | Key ROI value realized |  |  | $30M in six months if we follow the plan
Formulas:
Target Date = WORKDAY([Target Date, row above],[Days ⤵])

## Copy of Mutual Action Plan - Sa (hidden)
MUTUAL ACTION PLAN |  |  | VALTRON & CBRIGHT G5 DEAL
What is this? We like to use these non-binding planners to stay ahead of the curve and make the process as smooth as possible for all parties. Feel free to share with anyone in your org. |  |  | Valtron Factory Initiative Kick off |  | 2023-08-08 | Jump to Team members
|  |  | First Revenue (estimated date) |  | 2023-09-19
|  |  | First milestone completed (estimated date) |  | 2023-04-24 | Questions?
|  |  | Go Live (estimated date) |  | 2023-07-21 | Call or email Tom W anytime
|  |  | Days to Go Live (calculated) |  | 63 | 503-415-1428, tom@cbright.com
|  |  | Typical Process Length (days) |  | 76
Target Date | Done | Days ⤵ | Milestone | Owner (Valtron) | Owner (Cbright) | Outcome / Notes
2023-04-24 | TRUE |  | Intros & fit | Paul | Tom | Discuss business challenges /opportunities & identify where Valtron can help
2023-04-28 | TRUE | 4 | Establish use case(s) |  |  | Deep dive into how Valtron's G5 network would reduce contractor churn at Cbright
2023-05-02 | TRUE | 2 | Present business case |  |  | Get feedback on the business case and present our proposal
2023-05-30 | TRUE | 20 | Preflight |  |  | Work with Cbright's technical team and identify potential integration or infrastructure issues in advance
2023-06-27 | TRUE | 20 | Final negotation & signatures |  |  | Contracts / payment details finalized.
2023-07-06 | TRUE | 7 | Implementation / integration |  |  | Cbright team works with Valtron counterparts to integrate & test implementation
2023-07-13 | TRUE | 5 | Onboarding |  |  | Team training & Customer Success plan finalized
2023-07-21 | FALSE | 6 | GO LIVE: Flip the switch!
2023-08-08 |  | 12 | Valtron Factory Initiative Kick off |  | EXTERNAL | EXTERNAL
2023-09-19 |  | 30 | First Date of Value |  |  | $500K savings in first 30 days
2024-05-28 |  | 180 | Key ROI value realized |  |  | $30M in six months if we follow the plan
Formulas:
Target Date = WORKDAY([Target Date, row above],[Days ⤵])

## Team Members (hidden)
TEAM MEMBERS |  | VALTRON & CBRIGHT G5 DEAL
VALTRON's TEAM | Role | Team member | Email | Phone | Notes
| Engineering Manager | Paul Jones
| Finance Manager | <TBD>
| IT Admin | <TBD>
| Legal Review | <TBD>
| <other> | <TBD>
| <other> | <TBD>
| <other> | <TBD>
CBRIGHT's TEAM | Role | NAME | Email | Phone | Notes
| Account Executive | Tom Williams | tom@cbright.com | 503-415-1428
| Director of Sales | Vicky Melfi | vickym@cbright.com
| Sales Engineer | Sam Morse | sam.morse@cbright.com
| Customer Success Manager | Kristen Chellis | kristenc@cbright.com
| Finance / Contracts | Erin Bastoen | erinb@cbright.com

## Mutual Action Plan - BigTime
Mutual Action Plan
HOW IT WORKS: Mutual Action Plans are project plans for software evaluation to ensure vendors are working to support your process at the same pace as you. The best way to use this template is to work backward and first identify your target go-live date and when you want people in the platform tracking time. From there, use each tab of the spreadsheet for each vendor you’re speaking with to see how the timeline plays out. This way if a vendor can’t support your timeline you’ll know early on, or if the timeline makes sense for both parties this tool will help you keep track of your agenda.
Value Summary: Brief summary of the value and need-pay-off that you're looking to get out of a new solution. |  |  | Key Milestones |  | Target Date
|  |  | Finance/Account System |  | 0 | Questions?
|  |  | Other Key Integrations |  | 0 | Call or email (Rep Name)
|  |  | Important Customer milestones |  | 0 | Phone
|  |  | Go Live (estimated date) |  | 0 | Email
Days to Go Live
TARGET DATE | DONE | Days ⤵ | MILESTONE | OWNER | BigTime | OUTCOME / NOTES
|  |  | Introductions |  |  | Discuss business challenges /opportunities & identify where BigTime Software can help
|  |  | Demonstration |  |  | Initial Demonstration and discussion on user counts
|  |  | High-level Pricing and Implementation Discusion |  |  | Initial review of the total investment into BigTime and you'll be supported through implementation
|  |  | Business Case/Worklfow Validation |  |  | Product demonstrations to focus on key business workflows
Proof of Concept Kickoff
Proof of Concept Wrap Up
|  |  | Finalize Partnership |  |  | Contracts / payment details finalized.
|  |  | Implementation Kickoff Meeting |  |  | Introduction to dedicated Implementation Manager to lay foundation and schedule initial implementation calls.
|  |  | Onboarding |  |  | Team training & Customer Success plan finalized
|  |  | GO LIVE: Flip the switch! |  |  | Go Live Target

## Vendor 2
Mutual Action Plan | [5 empty] | [Vendor Name]
Value Summary: Brief summary of the value and need-pay-off that you're looking to get out of a new solution. |  |  | Key Milestones |  | Target Date
|  |  | Finance/Account System |  | 0 | Questions?
|  |  | Other Key Integrations |  | 0 | Call or email (Rep Name)
|  |  | Important Customer milestones |  | 0 | Phone
|  |  | Go Live (estimated date) |  | 0 | Email
Days to Go Live
TARGET DATE | DONE | Days ⤵ | MILESTONE | OWNER | BigTime | OUTCOME / NOTES
|  |  | Introductions |  |  | Discuss business challenges /opportunities & identify where BigTime Software can help
|  |  | Demonstration |  |  | Initial Demonstration and discussion on user counts
|  |  | HIgh-level Pricing and Implementation Discusion |  |  | Initial review of the total investment into BigTime and you'll be supported through implementation
|  |  | Business Case/Worklfow Validation |  |  | Product demonstrations to focus on key business workflows
Proof of Concept Kickoff
Proof of Concept Wrap Up
|  |  | Finalize Partnership |  |  | Contracts / payment details finalized.
|  |  | Implementation Kickoff Meeting |  |  | Introduction to dedicated Implementation Manager to lay foundation and schedule initial implementation calls.
|  |  | Onboarding |  |  | Team training & Customer Success plan finalized
|  |  | GO LIVE: Flip the switch! |  |  | Go Live Target

## Vendor 3
Mutual Action Plan | [5 empty] | [Vendor Name]
Value Summary: Brief summary of the value and need-pay-off that you're looking to get out of a new solution. |  |  | Key Milestones |  | Target Date
|  |  | Finance/Account System |  | 0 | Questions?
|  |  | Other Key Integrations |  | 0 | Call or email (Rep Name)
|  |  | Important Customer milestones |  | 0 | Phone
|  |  | Go Live (estimated date) |  | 0 | Email
Days to Go Live
TARGET DATE | DONE | Days ⤵ | MILESTONE | OWNER | BigTime | OUTCOME / NOTES
|  |  | Introductions |  |  | Discuss business challenges /opportunities & identify where BigTime Software can help
|  |  | Demonstration |  |  | Initial Demonstration and discussion on user counts
|  |  | HIgh-level Pricing and Implementation Discusion |  |  | Initial review of the total investment into BigTime and you'll be supported through implementation
|  |  | Business Case/Worklfow Validation |  |  | Product demonstrations to focus on key business workflows
Proof of Concept Kickoff
Proof of Concept Wrap Up
|  |  | Finalize Partnership |  |  | Contracts / payment details finalized.
|  |  | Implementation Kickoff Meeting |  |  | Introduction to dedicated Implementation Manager to lay foundation and schedule initial implementation calls.
|  |  | Onboarding |  |  | Team training & Customer Success plan finalized
|  |  | GO LIVE: Flip the switch! |  |  | Go Live Target

## Vendor 4
Mutual Action Plan | [5 empty] | [Vendor Name]
Value Summary: Brief summary of the value and need-pay-off that you're looking to get out of a new solution. |  |  | Key Milestones |  | Target Date
|  |  | Finance/Account System |  | 0 | Questions?
|  |  | Other Key Integrations |  | 0 | Call or email (Rep Name)
|  |  | Important Customer milestones |  | 0 | Phone
|  |  | Go Live (estimated date) |  | 0 | Email
Days to Go Live
TARGET DATE | DONE | Days ⤵ | MILESTONE | OWNER | BigTime | OUTCOME / NOTES
|  |  | Introductions |  |  | Discuss business challenges /opportunities & identify where BigTime Software can help
|  |  | Demonstration |  |  | Initial Demonstration and discussion on user counts
|  |  | HIgh-level Pricing and Implementation Discusion |  |  | Initial review of the total investment into BigTime and you'll be supported through implementation
|  |  | Business Case/Worklfow Validation |  |  | Product demonstrations to focus on key business workflows
Proof of Concept Kickoff
Proof of Concept Wrap Up
|  |  | Finalize Partnership |  |  | Contracts / payment details finalized.
|  |  | Implementation Kickoff Meeting |  |  | Introduction to dedicated Implementation Manager to lay foundation and schedule initial implementation calls.
|  |  | Onboarding |  |  | Team training & Customer Success plan finalized
|  |  | GO LIVE: Flip the switch! |  |  | Go Live Target

## Vendor 5
Mutual Action Plan | [5 empty] | [Vendor Name]
Value Summary: Brief summary of the value and need-pay-off that you're looking to get out of a new solution. |  |  | Key Milestones |  | Target Date
|  |  | Finance/Account System |  | 0 | Questions?
|  |  | Other Key Integrations |  | 0 | Call or email (Rep Name)
|  |  | Important Customer milestones |  | 0 | Phone
|  |  | Go Live (estimated date) |  | 0 | Email
Days to Go Live
TARGET DATE | DONE | Days ⤵ | MILESTONE | OWNER | BigTime | OUTCOME / NOTES
|  |  | Introductions |  |  | Discuss business challenges /opportunities & identify where BigTime Software can help
|  |  | Demonstration |  |  | Initial Demonstration and discussion on user counts
|  |  | HIgh-level Pricing and Implementation Discusion |  |  | Initial review of the total investment into BigTime and you'll be supported through implementation
|  |  | Business Case/Worklfow Validation |  |  | Product demonstrations to focus on key business workflows
Proof of Concept Kickoff
Proof of Concept Wrap Up
|  |  | Finalize Partnership |  |  | Contracts / payment details finalized.
|  |  | Implementation Kickoff Meeting |  |  | Introduction to dedicated Implementation Manager to lay foundation and schedule initial implementation calls.
|  |  | Onboarding |  |  | Team training & Customer Success plan finalized
|  |  | GO LIVE: Flip the switch! |  |  | Go Live Target

## Vendor 6
Mutual Action Plan | [5 empty] | [Vendor Name]
Value Summary: Brief summary of the value and need-pay-off that you're looking to get out of a new solution. |  |  | Key Milestones |  | Target Date
|  |  | Finance/Account System |  | 0 | Questions?
|  |  | Other Key Integrations |  | 0 | Call or email (Rep Name)
|  |  | Important Customer milestones |  | 0 | Phone
|  |  | Go Live (estimated date) |  | 0 | Email
Days to Go Live
TARGET DATE | DONE | Days ⤵ | MILESTONE | OWNER | BigTime | OUTCOME / NOTES
|  |  | Introductions |  |  | Discuss business challenges /opportunities & identify where BigTime Software can help
|  |  | Demonstration |  |  | Initial Demonstration and discussion on user counts
|  |  | HIgh-level Pricing and Implementation Discusion |  |  | Initial review of the total investment into BigTime and you'll be supported through implementation
|  |  | Business Case/Worklfow Validation |  |  | Product demonstrations to focus on key business workflows
Proof of Concept Kickoff
Proof of Concept Wrap Up
|  |  | Finalize Partnership |  |  | Contracts / payment details finalized.
|  |  | Implementation Kickoff Meeting |  |  | Introduction to dedicated Implementation Manager to lay foundation and schedule initial implementation calls.
|  |  | Onboarding |  |  | Team training & Customer Success plan finalized
|  |  | GO LIVE: Flip the switch! |  |  | Go Live Target